|  | S.S.V.P.S’s Bapusaheb Shivajirao Deore Polytechnic, Dhule |  |
| --- | --- | --- |

(Institute Code: 0059)

DEPARTMENT OF COMPUTER ENGINEERING

DAILY DIARY

Seminar Presentation and Project Initiation (SPI)

Course Code: 315003

| Name of Student | Mr. Sharma Nilesh Ashok |
| --- | --- |
| Enrollment Number | 24610960271 |
| Exam Seat Number | 388572 |
| Roll Number | 85 |
| Class / Semester | CO5K (Third Year, Fifth Semester) |
| Academic Year | 2026 – 2027 |
| Seminar Topic | Smart Inventory Management System using IoT and AI/ML |
| Name of Guide | Prof. N. D. Patel |

Group Members

| Sr. No. | Enrollment No. | Seat No. | Name of Student |
| --- | --- | --- | --- |
| 1 | 24610960269 | 388570 | Shaikh Mohammad Zakariya Haffizuddin |
| 2 | 24610960270 | 388571 | Shaikh Suher Rayaz |
| 3 | 24610960271 | 388572 | Sharma Nilesh Ashok |
| 4 | 24610960300 | 388599 | Ansari Zeeshan Habib |

PLAN OF WORK

| Phase | Duration | Activity |
| --- | --- | --- |
| 1 | 07/09/2026 – 25/09/2026 | Orientation, study of emerging technologies, topic selection |
| 2 | 26/09/2026 | Topic finalized: Smart Inventory Management using IoT and AI/ML |
| 3 | 26/09/2026 – 08/10/2026 | Searching, reading and comparing research papers (3 papers per member) |
| 4 | 08/10/2026 – 16/10/2026 | Preparation of SPI report and seminar presentation (PPT) |
| 5 | 17/10/2026 – 19/10/2026 | Corrections by course instructor, rehearsal and seminar presentation (19/10/2026) |

My research papers (3 of the 12 papers reviewed by the group):

1. Yu, Y. (2025), “Optimizing Supply Chain Logistics with IoT and Machine Learning: From Data Collection to Decision Making Based on Refined Battle Royale Optimizer Weighted Random Forest,” Informatica, 49(18), pp. 39–50.

2. Singh, S., Khatri, V., Ranjan, H., Agarwal, A. K., Hussain, S. and Garg, P. (2024), “Inventory Management Using Big Data and Internet of Things,” Indira Gandhi Delhi Technical University for Women, pp. 1–8.

3. Saxena, M., Verma, B., Sharma, N. and Tiwari, A. (2025), “Smart Inventory Management System Using Machine Learning,” GLIMPSE – Journal of Computer Science, 4(2), pp. 27–30.

My role in the group:

• Searched and studied 3 of the 12 research papers (listed above), covering IoT supply chain demand forecasting with RBRO-WRF, Big Data and IoT smart shelves for perishable inventory, and ML-based stock monitoring with AWS cloud.

• Compiled and formatted the SPI report: abstract, introduction, literature review, comparison table, diagrams, project initiation, bibliography and references.

• Prepared the seminar presentation (PPT) in the college format, matching the content and references of the report.

• Made the corrections suggested by the course instructor in the report and PPT.

• Presented slides 10, 11 and 12 in the seminar and answered the questions related to my part.

DAILY WORK RECORD

| Sr. No. | Date / Day | Work Done / Activity | Outcome | Guide’s Sign |
| --- | --- | --- | --- | --- |
| 1 | 07/09/2026 Monday | Participated in the orientation session for the SPI course (315003). Understood the course goals, the seminar and project initiation steps, maintaining the daily diary and the evaluation scheme. | Clear idea of SPI requirements |  |
| 2 | 09/09/2026 Wednesday | Formed our group with Zakariya, Suher and Zeeshan. Discussed each member’s field of interest and agreed to choose a topic from emerging technologies. | Group of 4 formed |  |
| 3 | 11/09/2026 Friday | Explored a list of emerging technologies including AI/ML, IoT, Blockchain, Cloud Computing and AR/VR, and read introductory articles on each of them. | Overview of emerging technologies |  |

Week 1 – Remarks of Guide: ______________________________________________________

| Sr. No. | Date / Day | Work Done / Activity | Outcome | Guide’s Sign |
| --- | --- | --- | --- | --- |
| 4 | 14/09/2026 Monday | Conducted a group brainstorming session on topics based on real-life problems. Topics explored: Brain Computer Interface, Smart Waste Detection and Management, Smart Traffic Management and Smart Inventory Management. | 4 topics listed |  |
| 5 | 16/09/2026 Wednesday | Studied the fundamentals of IoT: sensors, microcontroller boards (ESP32, NodeMCU, Raspberry Pi), RFID and how connected devices transmit data over Wi-Fi. | Basic understanding of IoT |  |
| 6 | 18/09/2026 Friday | Studied the fundamentals of Machine Learning: supervised learning, regression models, decision trees and how inventory demand forecasting works. | Basic understanding of ML |  |

Week 2 – Remarks of Guide: ______________________________________________________

| Sr. No. | Date / Day | Work Done / Activity | Outcome | Guide’s Sign |
| --- | --- | --- | --- | --- |
| 7 | 21/09/2026 Monday | Analyzed and compared the four topics (BCI, Smart Waste, Smart Traffic, Smart Inventory) based on their usefulness, availability of research papers and feasibility as a diploma-level project. | Topics compared |  |
| 8 | 23/09/2026 Wednesday | Examined the problems of manual inventory (stock registers, physical counting) in college labs and small shops; noted that stock-outs, over-stocking and misplaced items occur frequently. | Problem area identified |  |
| 9 | 25/09/2026 Friday | Prepared a short proposal for the selected topic and discussed it with our guide. | Proposal discussed with guide |  |
| 10 | 26/09/2026 Saturday | Topic finalized: “Smart Inventory Management System using IoT and AI/ML” was approved by the guide. | Topic approved |  |

Week 3 – Remarks of Guide: ______________________________________________________

| Sr. No. | Date / Day | Work Done / Activity | Outcome | Guide’s Sign |
| --- | --- | --- | --- | --- |
| 11 | 28/09/2026 Monday | Learned how to search for research papers on Google Scholar, IEEE Xplore and ResearchGate. Listed search keywords: IoT inventory, RFID, Big Data, Random Forest, demand forecasting. | Search method decided |  |
| 12 | 29/09/2026 Tuesday | Divided the work in the group: every member had to find and study 3 research papers, covering scales from large industry down to a small department. | Work divided |  |
| 13 | 30/09/2026 Wednesday | Found and read my 1st paper: Yu (2025) – IoT and ML supply chain logistics optimization using the Refined Battle Royale Optimizer Weighted Random Forest (RBRO-WRF) model. | Paper 1 read |  |
| 14 | 01/10/2026 Thursday | Made notes on Paper 1: IoT sensors (RFID, GPS, temperature, humidity), Kaggle supply chain dataset, Min-Max and Z-score normalization in Python; RBRO-WRF achieved 3.41% MAPE and 0.00324 MSE. | Notes on Paper 1 |  |
| 15 | 03/10/2026 Saturday | Found and read my 2nd paper: Singh et al. (2024) – Inventory management using IoT (RFID tags, smart shelves, weight and temperature sensors) and Big Data analytics; Random Forest Regressor gave an R² score of 0.85. | Paper 2 read |  |

Week 4 – Remarks of Guide: ______________________________________________________

| Sr. No. | Date / Day | Work Done / Activity | Outcome | Guide’s Sign |
| --- | --- | --- | --- | --- |
| 16 | 05/10/2026 Monday | Found and read my 3rd paper: Saxena et al. (2025) – Smart inventory system using Random Forest and IoT sensors with AWS S3/EC2 cloud; achieved 30% higher stock accuracy and 25% cost reduction. | Paper 3 read; ML models compared |  |
| 17 | 06/10/2026 Tuesday | Group meeting held: compiled all 12 papers, finalized them and arranged them in order from large industry to small lab. | 12 papers finalized |  |
| 18 | 07/10/2026 Wednesday | Created the literature comparison covering the approach, technologies, dataset, key objective and limitations of every paper. | Literature table drafted |  |
| 19 | 08/10/2026 Thursday | Identified the research gap: low-cost systems only track stock, whereas forecasting-based systems are expensive. Completed the literature survey. | Research gap identified |  |

Week 5 – Remarks of Guide: ______________________________________________________

| Sr. No. | Date / Day | Work Done / Activity | Outcome | Guide’s Sign |
| --- | --- | --- | --- | --- |
| 20 | 09/10/2026 Friday | Reviewed the college report format and a sample report of another group; finalized the chapters, fonts and page layout. | Report format fixed |  |
| 21 | 10/10/2026 Saturday | Prepared the Abstract and the Introduction chapter of the SPI report. | Chapter 1 drafted |  |
| 22 | 12/10/2026 Monday | Prepared the Literature Review chapter along with Table 2.1 (comparison of the 12 papers). | Chapter 2 drafted |  |
| 23 | 13/10/2026 Tuesday | Prepared the Information chapter on the roles of IoT and AI/ML; designed the working flowchart (Fig 3.1) and the system architecture diagram (Fig 3.2). | Chapter 3 and diagrams |  |
| 24 | 14/10/2026 Wednesday | Prepared the Advantages/Disadvantages, Conclusion and Project Initiation (problem statement, scope, objectives, stakeholders, platform and resources) chapters. | Chapters 4–6 drafted |  |
| 25 | 15/10/2026 Thursday | Compiled the Bibliography and References; started the seminar presentation (PPT) in the college format. | Bibliography and PPT started |  |
| 26 | 16/10/2026 Friday | Completed the PPT and reviewed the report and PPT together with the group. Printed and submitted both the SPI report and the PPT. | Report and PPT submitted |  |

Week 6 – Remarks of Guide: ______________________________________________________

| Sr. No. | Date / Day | Work Done / Activity | Outcome | Guide’s Sign |
| --- | --- | --- | --- | --- |
| 27 | 17/10/2026 Saturday | Implemented the corrections suggested by the course instructor: table headers, justified alignment, Kevin Ashton’s contribution in the Introduction, and page-wise references to the research papers. (Term end) | Report corrected |  |
| 28 | 18/10/2026 Sunday | Added reference numbers to the PPT points and diagrams; checked consistency and page numbers of the report; rehearsed my part (slides 10–12) and prepared for viva questions. | Final report and PPT ready |  |
| 29 | 19/10/2026 Monday | Seminar presentation (19/10/2026): presented my part of the seminar (slides 10, 11 and 12) and answered the questions asked. | Seminar presented |  |

Week 7 – Remarks of Guide: ______________________________________________________

LEARNING OUTCOMES

• Learned how to select a seminar topic from emerging technologies based on a real-life problem.

• Learned to search, read and compare research papers using Google Scholar, IEEE Xplore and ResearchGate.

• Understood how IoT devices (RFID, load cell, ESP32) track inventory in real time.

• Understood how Machine Learning models such as Random Forest forecast demand.

• Learned to identify a research gap and define a problem statement, scope and objectives.

• Learned to prepare a technical report with proper format, figures, tables and references.

• Improved presentation and communication skills through the seminar and viva.

Other learning: Practical working of RFID (RC522 reader and tags), the ESP32 microcontroller, and the Random Forest model in AI/ML for demand prediction.

| Signature of Student | Signature of Guide |
| --- | --- |
| Name: Mr. Sharma Nilesh Ashok | Name: Prof. N. D. Patel |
| Date: ______________ | Date: ______________ |

Signature of Head of Department: ______________________